## Slide 1
1
Anunta – Weekly Status Report
3rd May 2019
Prepared for Anunta
Notes: 1

## Slide 2
Timelines (Originally proposed)
Weekly Status
Issue Tracker
Agenda
1

## Slide 3
Timeline (Originally proposed)
Activity | Deliverable | Weeks
Understanding data | Cassandra tables exploration, Domain, System Architecture , EUVantage | Week 1 & Week 2 (April 1 till April 12)
Data cleaning | Imputation of missing values . Changing data to a format that can be used for further analysis. | Week 3 (April 15 till April 26)
Univariate Analysis | Univariate graphs and corresponding analysis | Week 3 (29th April – In Progress)
Multivariate Analysis | Multivariate graphs and corresponding analysis | Week 4
Hypothesis Testing | Proving Inferences from earlier analysis. | Week 4 & Week 5
Feature Engineering and Feature Selection |  | To be decided after completion of Hypothesis Testing
Models And Algorithms |  | To be decided after completion of Hypothesis Testing
Issue Tracker
Weekly Status
Timeline
1
Notes: 1

## Slide 4
Project status this week
Project Week | Accomplishments till now | Next steps | Task Owner | Start Date | End Date
29th April- 3rd Mayl | Univariate Analysis parameters. | Analyzing ATMSL customer Data | Sathvi S | 6th May | 10th May
 | Normalising data for metrics – Availability and Packet loss for ATMSL . |  | Ashish Sethia | 6th May | 10th May
Issue Tracker
Weekly Status
Timeline
1

## Slide 5
1
Issue/Risk tracker
Issue Log Date | Issue | Impact on the project | Raised by | Clarification | Clarified by | Clarified Date | Status | Type
17th April | Coding in VI / No IDE | Makes writing code a very tedious process and delays the coding process. | Ashish | Access to Jupyter Notebook | Bharath | 29th April | Closed | 
22nd April | Increased CPU utilization when two people logs in together | Reduces the speed of work | Ashish | New VM has been created | Bharath | 29th April | Closed | 
22nd April | Access to new VM | Not able to proceed with EDA | Ashish | New VM has been created | Bharath | 29th April | Closed | 
11th April​ | Citrix Receiver Access issue​ | Not able to connect to Cassandra DB and start with EDA | Ashish | Access Issue Resolved | Bharath | 15th April | Closed | 
Issue Tracker
Weekly Status
Timeline
1

## Slide 6
Thank You !
1
Notes: 1